## ClientSecurityHash
ProcessName RPA Implementation Plan
Task Category |  |  | Owner | Start Date | End Date | Start time EST | End Time | Duration | Comments | Links
Pre-Release |  | 1. UAT Testing - 2. Submit CR - NA 3. Submit Deployment Request
Deployment
Click On tenent Click on packges Click on upload package button upload nuget package
| PD1 | Verify Package
Under MANAGEMENT section Click on PACKAGES
Locate the PackageName process and match the version
Create Process
|  | Under PROCESSES section click on + | Calculate Client security hash
Select PackageName from Package Name dropdown
Select Package from Environment dropdown
In the display name "Calculate client security hash"
Add New Assets (total 17 new assets)
|  | Asset Name | Asset Type | Asset Value (1. = username 2. = Password)
| 1 | acme_credential | Credentials | True
Create Trigger
|  | Under AUTOMATIONS section, Select TRIGGERS | No Triggers
Provide below values: Select Trigger Type: Time Name: TriggerName Process: ProcessName Schedule : Add Schedule Click on ADD button
Test Process
Under MONITORING section Click on JOBS
locate JobName
Click the checkbox next to the Robot
Click the Start
|  | Enable Scheduler: | No schedular required
Under AUTOMATIONS section, Select TRIGGERS
Locate TriggerName
Click the checkbox next to the schedule name
click the Enable button above the schedules list

## Backout Plan
Backout Plan
Task # | App | Tasks | Owner | Date | Start Time EDST | Duration
Disable Triggers

## Release Issues
Issue # | Date | Release | Reporter | Resolved by: | Application(s) | Env | Issue | Error received | Root Cause | Short term Resolution/ Work around | Long term solution
no issues